## Sheet1
工卡描述(中文) | 工卡描述(英文) | 参考工卡 | 工卡指令号 | 持卡人 | 创建日期
驾驶舱正、副驾驶员座椅套破损。 | THE SEAT COVERS ON COCKPIT CAPTAIN SEAT AND F/O SEAT DAMAGED. | 预检项目/PRE-CHECK ITEM | 500000337641 | 001909伍文海 | 2014-04-23 10:57
驾驶舱第3、4观察员座椅座椅套破损。 | THE SEAT COVERS ON COCKPIT 3RD AND 4TH OBSERVER SEATS DAMAGED. | 预检项目/PRE-CHECK ITEM | 500000337645 | 002257李锐明 | 2014-04-23 11:00
驾驶舱第4观察员座椅坐垫海绵破损 | THE SEAT-PAN CUSHION ON COCKPIT 4TH OBSERVER SEAT DAMAGED. | 预检项目/PRE-CHECK ITEM | 500000337647 | 002257李锐明 | 2014-05-14 09:50
客舱乘务员座椅座椅套有色差,位置:前左左,前左右,中前左,中后右,后左,后中过道,后右。 | THE SEAT COVERS ON CABIN ATTENDANT SEATS HAVE ABERRATION,LOC:FWD LH/LH,FWD LH/RH,MID FWD LH,MID AFT RH,AFT LH,AFT MID AISLE,AFT RH. | 预检项目/PRE-CHECK ITEM | 500000337658 | 002257李锐明 | 2014-04-25 10:26
客舱G8厨房工作台台面边条封严破损。 | THE EDGE STRIP SEAL ON CABIN GALLEY G8 WORK DECK TOPS DAMAGED. | 预检项目/PRE-CHECK ITEM | 500000337767 | 001909伍文海 | 2014-04-23 11:25
客舱右前储物柜前表面镜子划花。 | THE SURFACE MIRROR ON CABIN RH FWD CLOSET SCRATCHED. | 预检项目/PRE-CHECK ITEM | 500000337805 | 005696李浩荣 | 2014-04-23 12:50
客舱大门门框把手破损。 | THE DOORFRAME HANDLES ON CABIN DOORS DAMAGED. | 预检项目/PRE-CHECK ITEM | 500000337807 | 001909伍文海 | 2014-04-23 12:54
客舱公务舱头排前杂志袋老化,数量:4EA。 | THE FWD LITERATURE POCKETS ON CABIN B/C IAT AGED,QTY:4EA. | 预检项目/PRE-CHECK ITEM | 500000337809 | 001909伍文海 | 2014-04-23 12:57
客舱经济舱头排前杂志袋老化,数量:12EA。 | THE FWD LITERATURE POCKETS ON CABIN E/C IAT AGED,QTY:12EA. | 预检项目/PRE-CHECK ITEM | 500000337811 | 001909伍文海 | 2014-04-23 12:59
客舱A厕所纸盒外盖有裂纹,数量:1EA。 | THE PAPERBOX COVER ON CABIN LAVATORY A HAS CRACKS,QTY:1EA. | 预检项目/PRE-CHECK ITEM | 500000337812 | 001909伍文海 | 2014-04-23 13:03
驾驶舱门后锁盖装饰板颜色不一致。 | THE AFT LOCK COVER FAIRINGS ON COCKPIT DOOR DIFFERED. | 预检项目/PRE-CHECK ITEM | 500000337813 | 001909伍文海 | 2014-04-23 13:06
拆卸/安装客舱右前储物柜 | REMOVE/INSTALL THE CABIN RH-FWD STOWAGE ASSY | 20PANEL-230-1-1 | 500000343163 | 000670杨伟南 | 2014-04-29 09:19
拆卸/安装客舱左右前隔板 | REMOVE/INSTALL CABIN LH-FWD AND RH-FWD CLASS DIVIDER | 20PANEL-240-1-1 | 500000343177 | 001909伍文海 | 2014-04-29 09:38
客舱A、D、E、H厕所马桶罩划伤 | THE CABIN LAV A、D、E、H TOILET SHROUD SCRATCHED | A20M2500506-1 | 500000343826 | 002263刘永俊 | 2014-04-29 14:57
客舱A厕所垃圾箱门破损 | THE WASTE BIN DOOR OF CABIN LAV A DAMAGED | A20M2500506-1 | 500000343833 | 001909伍文海 | 2014-04-29 14:59
客舱H厕所垃圾箱门破损 | THE WASTE BIN DOOR OF CABIN LAV H DAMAGED | A20M2500506-1 | 500000343863 | 001909伍文海 | 2014-04-29 15:17
客舱H厕所马桶罩坐垫板破损 | THE TOILET SEAT ASSY OF CABIN LAV H DAMAGED | A20M2500506-1 | 500000343895 | 003917刘伟勋 | 2014-04-29 15:24
客舱前服务区地板胶破损 | CABIN FWD UTILITY AREA FLOOR MAT BROKEN | A20M2500506-1 | 500000344013 | 000670杨伟南 | 2014-04-29 16:11
客舱中服务区地板胶破损 | CABIN MID UTILITY AREA FLOOR MAT BROKEN | A20M2500506-1 | 500000344014 | 001909伍文海 | 2014-04-29 16:12
客舱后服务区地板胶破损 | CABIN AFT UTILITY AREA FLOOR MAT BROKEN | A20M2500506-1 | 500000344016 | 001909伍文海 | 2014-04-29 16:13
客舱左右1#门边衬板表面划伤 | THE FRAME LINING OF CABIN LH1# AND RH1# DOOR SCRATCHED | A20M2500506-1 | 500000344314 | 004355苏勇洲 | 2014-04-30 08:31
拆卸/安装客舱后区左右狗屋 | REMOVE/INSTALL LH AND RH DOG HOUSE OF CABIN AFT AREA | A20M2500506-1 | 500000344341 | 001909伍文海 | 2014-04-30 09:00
驾驶舱副驾驶脚踏板上的胶皮破损 | COCKPIT CO-PILOT FOOT-REST RUBBER DAMAGED | A20M2500506-1 | 500000344349 | 001909伍文海 | 2014-04-30 09:14
客舱前厨房旋钮失效,备注:4EA | THE SINGLE REVOLVING CATCH OF CABIN FWD GALLEY DISABLE,REMARK:4EA | A20M2500506-1 | 500000344407 | 001909伍文海 | 2014-04-30 10:00
客舱头等舱座椅过道防撞条表面划花,座椅:1CH 2CH 3CH | THE AISLE BUMPERS SURFACE ON CABIN F/C SEAT SCRATCHED,SEAT:1CH 2CH 3CH | 预检项目/PRE-CHECK ITEM | 500000344421 | 002796叶宇辉 | 2014-04-30 10:09
客舱头等舱座椅侧扶手前端金属装饰板表面划花,座椅:1ACHK 2ACHK 3ACHK | THE FRONT METAL FAIRINGS SURFACE ON CABIN F/C SEAT SIDE ARMREST SCRATCHED,SEAT:1ACHK 2ACHK 3ACHK | 预检项目/PRE-CHECK ITEM | 500000344452 | 002796叶宇辉 | 2014-04-30 10:34
客舱左、右前隔板后表面墙纸破损。 | THE WALLPAPERS ON CABIN LH AND RH FWD PARTITIONS DAMAGED. | 预检项目/PRE-CHECK ITEM | 500000344493 | 000655苏锦德 | 2014-04-30 10:37
客舱地板应急荧光条老化,备注:FR20-FR66 | THE EMER ESCAPE PATH MARKING OF CABIN FLOOR AGEING,REMARK:FR20-FR66 | A20M2500506-1 | 500000344588 | 001909伍文海 | 2014-04-30 11:18
客舱头等舱座椅侧扶手盖板破损、划花,座椅:1ACHK 2ACHK 3ACHK | THE SIDE ARMCAPS ON CABIN F/C SEAT DAMAGED OR SCRATCHED,SEAT:1ACHK 2ACHK 3ACHK | A20M2500506-1 | 500000344644 | 004580聂磊 | 2014-05-03 11:46
客舱头等舱座椅中扶手托盘装饰板破损,座椅:L1 L2 L3 R1 R2 R3 | THE CENTER ARMREST TRAY DECORATIVE PLATES ON CABIN F/C SEAT DAMAGED,SEAT:L1 L2 L3 R1 R2 R3 | A20M2500506-1 | 500000344646 | 002796叶宇辉 | 2014-05-03 11:46
客舱头等舱座椅中扶手盖板破损,座椅:L1 L2 L3 R1 R2 R3 | THE CENTER ARMCAP ON CABIN F/C SEAT DAMAGED,SEAT:L1 L2 L3 R1 R2 R3 | A20M2500506-1 | 500000344648 | 002796叶宇辉 | 2014-05-03 11:46
客舱头等舱座椅脚损坏,座椅:L2 | THE FOOT ON CABIN F/C SEAT DAMAGED,SEAT:L2 | A20M2500506-1 | 500000344655 | 002796叶宇辉 | 2014-05-03 11:45
客舱经济舱座椅脚损坏,座椅:L32 | THE FOOT ON CABIN E/C SEAT DAMAGED,SEAT:L32 | A20M2500506-1 | 500000344656 | 002796叶宇辉 | 2014-04-30 13:01
客舱座椅安全带脏,座椅:31ABCHJK-58ABCHJK | THE SAFETY BELTS ON CABIN SEAT DIRTY,SEAT:31ABCHJK-58ABCHJK | A20M2500506-1 | 500000344662 | 002796叶宇辉 | 2014-04-30 13:09
客舱座椅安全带损坏,座椅:1ACHK 32J 35C 36ACK 44K 45K 47K 48AC 49K 51CJK 52BJ 53K 55C 57C 58J | THE SAFETY BELTS ON CABIN SEAT DAMAGED,SEAT:1ACHK 32J 35C 36ACK 44K 45K 47K 48AC 49K 51CJK 52BJ 53K 55C 57C 58J | A20M2500506-1 | 500000344666 | 002796叶宇辉 | 2014-04-30 13:13
客舱58HJK侧壁板内窗框破损 | THE FRAME ASSY-DECOR OF CABIN 58HJK SIDEWALL PANEL DAMAGED | A20M2500506-1 | 500000344668 | 001909伍文海 | 2014-04-30 13:17
客舱乘务员座椅表面脏,座椅:前左左,前左右,中前左,中后右,后左,后中过道,后右。 | THE SURFACE ON CABIN ATTENDANT SEATS DIRTY,SEAT:FWD LH/LH,FWD LH/RH,MID FWD LH,MID AFT RH,AFT LH,AFT MID AISLE,AFT RH. | A20M2500506-1 | 500000344669 | 002257李锐明 | 2014-04-30 13:19
客舱乘务员座椅表面划伤,座椅:前左左,前左右,中前左,中后右,后左,后中过道,后右。 | THE SURFACE ON CABIN ATTENDANT SEAT SCRATCHED,SEAT:FWD LH/LH,FWD LH/RH,MID FWD LH,MID AFT RH,AFT LH,AFT MID AISLE,AFT RH. | A20M2500506-1 | 500000344673 | 000504米远君 | 2014-04-30 13:20
客舱行李箱门外表面破损,备注:R3 L35 L46 L57 R56 | THE OUTSIDE SURFACE OF CABIN OVERHEAD STOWAGE BIN DOOR DAMAGED,REMARK:R3 L35 L46 L57 R56 | A20M2500506-1 | 500000344677 | 001909伍文海 | 2014-04-30 13:24
客舱行李箱门内表面划伤,备注:L3 L31 R35 L36 R41 R43 R45 R52 L56 L57 | THE INSIDE SURFACE OF CABIN OVERHEAD STOWAGE BIN DOOR SCRATCHED,REMARK:L3 L31 R35 L36 R41 R43 R45 R52 L56 L57 | A20M2500506-1 | 500000344682 | 001909伍文海 | 2014-04-30 13:27
客舱乘务员座椅安全带起毛,座椅:前左左,前左右,中前左,中后右,后左,后中过道,后右。 | THE SAFETY BELTS ON CABIN ATTENDANT SEATS FUZZY,SEAT:FWD LH/LH,FWD LH/RH,MID FWD LH,MID AFT RH,AFT LH,AFT MID AISLE,AFT RH. | A20M2520512-1 | 500000344683 | 002257李锐明 | 2014-04-30 13:29
方向舵钢索张力调节器标记不在范围内. | INDICATION POINTER ON CABLE TENSION REGULATOR OF RUDDER OUT OF THE LIMIT. | A20J272145-01-1 | 500000344821 | 001639周卫 | 2014-04-30 15:06
客舱H厕所下橱柜破损 | THE LWR PART CABINET-SERVICE OF CABIN LAV H DAMAGED | A20M2500506-1 | 500000344956 | 001909伍文海 | 2014-04-30 16:06
客舱天花板破损,备注:231JC,251GC | CABIN CEILING PANELS DAMAGE.REMARK:231JC,251GC | A20M2500506-1 | 500000344964 | 002207黄伟健 | 2014-04-30 16:08
客舱天花板安装销断,备注:231JC,1EA | CABIN CEILING PAENL INSTALL PIN BREAK,REMARK:231JC,1EA | A20M2500506-1 | 500000344966 | 004494潘宏达 | 2014-04-30 16:09
客舱行李架门门锁破损,备注:FR48,L/H | CABIN OVERHEAD STOWAGE DOOR LATCH DAMAGE,REMARK:FR48,L/H | A20M2500506-1 | 500000344985 | 001909伍文海 | 2014-04-30 16:16
客舱座椅扶手前端装饰板缺失,座椅:34ABC 36L 47L 49HJK 52LR 56J | THE FRONT FAIRING ON CABIN SEAT ARMREST MISSING,SEAT:34ABC 36L 47L 49HJK 52LR 56J | A20M2500506-1 | 500000345037 | 002796叶宇辉 | 2014-04-30 17:14
客舱H厕所洗手盆盖板破损 | THE PANEL ASSY-WASHBASIN UNIT OF CABIN LAV H DAMAGED | A20M2500506-1 | 500000345310 | 001909伍文海 | 2014-05-01 08:28
客舱G8厨房旋钮失效,备注:6EA | THE CATCH-SINGLE REVOLVING OF CABIN GALLEY 8 DISABLE,REMARK:6EA | A20M2500506-1 | 500000345317 | 001909伍文海 | 2014-05-01 08:37
客舱侧壁板标牌丢失,备注:FR35.7-FR36、FR45-FR47 | THE PLACARD OF CABIN SIDEWALL PANEL MISSING,REMARK:FR35.7-FR36、FR45-FR47 | A20M2500506-1 | 500000345321 | 001909伍文海 | 2014-05-01 08:45
客舱左右2#门上门框衬板快卸螺钉失效,备注:4EA | THE STUD ASSY OF CABIN LH2# AND RH2# DOOR UPSIDE FRAME LINING DISABLE,REMARK:4EA | A20M2500506-1 | 500000345330 | 002207黄伟健 | 2014-05-01 09:04
客舱左右2#门门框衬板上部接近盖板破损 | THE UPSIDE ACCESS PANEL OF CABIN LH 2# AND RH 2# DOOR FRAME LINING DAMAGED | A20M2500506-1 | 500000345342 | 001909伍文海 | 2014-05-01 09:15
客舱左右4#门框衬板表面划伤 | THE SURFACE OF CABIN LH 4# AND RH 4# DOOR FRAME LINING SCRATCHED | A20M2500506-1 | 500000345350 | 002207黄伟健 | 2014-05-01 11:06
客舱座椅扶手前盖板破损,备注:34B、38K、39C、40C、45A、47A、51H、52J、53H、55LK、57C,12EA | CABIN PASSENGER SEAT ARMREST FRONT CAP BROKEN, REMARK:34B、38K、39C、40C、45A、47A、51H、52J、53H、55LK、57C,12EA | A20M2500506-1 | 500000345354 | 002796叶宇辉 | 2014-05-01 09:41
客舱旅客座椅餐板不平,备注:R31-R58,数量:66EA | CABIN PASSENGER SEAT BACKMOUNTED FOODTABLE NOT LEVEL, REMARK:R31-R58, QTY:66EA | A20M2500506-1 | 500000345379 | 002796叶宇辉 | 2014-05-01 09:54
客舱旅客座椅餐板不平,备注:L31-L58,数量:62EA | CABIN PASSENGER SEAT BACKMOUNTED FOODTABLE NOT LEVEL, RAMARK:L31-L58,QTY:62EA | A20M2500506-1 | 500000345386 | 002796叶宇辉 | 2014-05-01 09:57
客舱座椅靠背不平,备注:R31-R58,数量:65EA | CABIN PASSENGER SEAT BACKREST NOT LEVEL, REMARK:R31-R58,QTY:65EA | A20M2500506-1 | 500000345404 | 002796叶宇辉 | 2014-05-01 10:08
客舱座椅靠背不平,备注:L31-L58,数量:67EA | CABIN PASSENGER SEAT BACKREST NOT LEVEL, REMARK: L31-L58,数量:67EA | A20M2500506-1 | 500000345405 | 002796叶宇辉 | 2014-05-01 10:10
客舱左右4#门框衬板堵盖丢失,备注:4EA | THE CAP OF CABIN LH4# AND RH4# DOOR FRAME LINING MISSING,REMARK:4EA | A20M2500506-1 | 500000345435 | 001909伍文海 | 2014-05-01 10:30
客舱头等舱旅客座椅SEB盒损坏,备注:6EA | CABIN F/C PASSENGER SEAT SEB BOX DAMAGE,REMARK:6EA | A20M2500506-1 | 500000345436 | 001909伍文海 | 2014-05-01 10:30
客舱座椅脚脏,备注:L1-L3,L31-L58 | CABIN PASSENGER SEAT INSTAL FITTING DIRTY, REMARK:L1-L3,L31-L58 | A20M2500506-1 | 500000345464 | 002796叶宇辉 | 2014-05-01 10:33
客舱座椅脚脏,备注:R1-R3,R31-R58 | CABIN PASSENGER SEAT INSTALL FITTING DIRTY, REMARK: R1-R3,R31-R58 | A20M2500506-1 | 500000345485 | 002796叶宇辉 | 2014-05-01 10:35
客舱经济舱旅客座椅SEB盒损坏,备注:L:13,R:13 | CABIN B/C PASSENGER SEAT SEB BOX DAMAGE,REMARK:L:13,R:13 | A20M2500506-1 | 500000345517 | 003915周永谦 | 2014-05-01 10:40
客舱头排座椅扶手掉漆,备注:31ABCHJK、35ABCHJK | THE PAINT COAT OF CABIN PASSENGER IAT SEAT ARMREST MISSING,REMARK:31ABCHJK、35ABCHJK | A20M2500506-1 | 500000345535 | 002796叶宇辉 | 2014-05-05 11:12
客舱乘务员座椅标牌破损 | CABIN ATTENDANT SEAT PLACARD BROKEN | A20M2520512-1 | 500000345569 | 002257李锐明 | 2014-05-01 10:52
客舱2#门乘务员座椅释放销及支架丢失 | CABIN 2# DOOR ATTENDANT SEAT OXYGEN RELEASE PIN AND BRACKET MISSING | A20M2520512-1 | 500000345604 | 002257李锐明 | 2014-05-01 11:23
客舱左前乘务员座椅柜门破损 | CABIN LH FWD ATTENDANT SEAT STOWAGE DOOR BROKEN | A20M2520512-1 | 500000345618 | 002257李锐明 | 2014-05-01 11:43
客舱左、右后乘务员座椅导向片破损,备注:4EA | CABIN LH AND RH AFT ATTENDANT SEAT PROTECTION PLATE BROKEN, REMARK:4EA | A20M2520512-1 | 500000345622 | 002257李锐明 | 2014-05-01 12:35
客舱经济舱旅客座椅扶手松动,数量:41EA,位置:33JR 33R 35LR 36R 37LAC 38B 39B 40R 41JR 42R 43L 45A 49BJ 50A 51JKR 52LBCJ 53R 54LK 55LCJ 56ABC 57A 58LBCJ | THE ARMREST OF CABIN Y/C SEAT LOOSEN,QUANTITY:41EA,LOCATION:33JR 33R 35LR 36R 37LAC 38B 39B 40R 41JR 42R 43L 45A 49BJ 50A 51JKR 52LBCJ 53R 54LK 55LCJ 56ABC 57A 58LBCJ | A20M2500506-1 | 500000345633 | 002796叶宇辉 | 2014-05-01 12:54
客舱经济舱旅客座椅作动筒失效,数量:8EA,位置:36B 38A 42J 43HJ 52A 53J 58B | THE HUDRAULIC LOCK OF CABIN Y/C SEAT FAILED,QUANTITY:8EA,LOCATION:36B 38A 42J 43HJ 52A 53J 58B | A20M2500506-1 | 500000345638 | 002796叶宇辉 | 2014-05-01 13:01
客舱经济舱旅客座椅控制钢索按钮卡阻,数量:1EA,位置:34A | THE BUTTON OF CABIN Y/C SEAT CONTROL CABLE JAMMED,QUANTITY:1EA,LOCATION:34A | A20M2500506-1 | 500000345641 | 002796叶宇辉 | 2014-05-01 13:05
客舱经济舱旅客座椅过道扶手下部装饰板破损,数量:4EA,位置:31H 34C 55C 57C | THE AISLE ENDBAY OF CABIN Y/C SEAT DAMAGED,QUANTITY:4EA,LOCATION:31H,34C,55C,57C | A20M2500506-1 | 500000345645 | 002796叶宇辉 | 2014-05-01 13:08
客舱经济舱旅客座椅餐板旋钮破损,数量:6EA,位置:37BC,47CJ,54A,58B | THE FOODTRAY ESCUTCHEON ASSY OF CABIN Y/C SEAT DAMAGED,QUANTITY:6EA,LOCATION:37BC,47CJ,54A,58B | A20M2500506-1 | 500000345648 | 002796叶宇辉 | 2014-05-01 13:12
客舱经济舱旅客座椅扶手后盖板破损,数量:20EA,位置:33C 36H 37H 38C 42C 44C 45H 48C 49C 51AH 52J 53BH 54CH 55CH 57H 58B | THE ARMCAP OF CABIN Y/C SEAT ARMREST DAMAGED,QUANTITY:20EA,LOCATION:33C 36H 37H 38C 42C 44C 45H 48C 49C 51AH 52J 53BH 54CH 55CH 57H 58B | A20M2500506-1 | 500000345654 | 002796叶宇辉 | 2014-05-01 13:15
客舱经济舱旅客座椅扶手锁扣断裂,数量:2EA,位置:40R 45L | THE LATCH ASSY OF CABIN Y/C SEAT ARMREST CRACKED, QUANTITY:2EA,LOCATION:40R 45L | A20M2500506-1 | 500000345658 | 002796叶宇辉 | 2014-05-01 13:19
客舱经济舱旅客座椅餐板破损,数量:56EA,位置:31JK 32HJ 33HJ 35AHK 36HJ 37H 38AJK 39C 40H 41BCHJK 42AHJK 43BHJK 44HJK 48A 49JK 51AHJK 52JK 53HJ 54ABK 56HJK 57AHJK 58CJ | THE BACK-MOUNTED FOODTRAY OF CABIN Y/C SEAT DAMAGED,QUANTITY:56EA,LOCATION:31JK 32HJ 33HJ 35AHK 36HJ 37H 38AJK 39C 40H 41BCHJK 42AHJK 43BHJK 44HJK 48A 49JK 51AHJK 52JK 53HJ 54ABK 56HJK 57AHJK 58CJ | A20M2500506-1 | 500000345660 | 001909伍文海 | 2014-05-01 13:23
客舱经济舱旅客座椅行李架挡条松动,数量:51EA,位置:L33-L58 R31-R45 R47-R56 | THE BAGGAGE BARS OF CABIN Y/C SEAT LOOSEN,QUANTITY:51EA,LOCATION:L33-L58 R31-R45 R47-R56 | A20M2500506-1 | 500000345662 | 004580聂磊 | 2014-05-01 13:25
客舱经济舱旅客座椅行李架挡条堵盖丢失,数量:57EA,位置:L2 L31-L58 R31-R58 | THE BAGGAGE BAR PLUG OF CABIN Y/C SEAT MISSED,QUANTITY:57EA,LOCATION:L2 L31-L58 R31-R58 | A20M2500506-1 | 500000345666 | 002796叶宇辉 | 2014-05-01 13:28
客舱左后乘务员座椅安装衬套腐蚀 | CABIN AFT LH ATTENDANT SEAT INSTALL BUSHING ROT | A20M2500506-1 | 500000345676 | 001909伍文海 | 2014-05-01 13:33
客舱G1厨房工作台表面鼓起 备注:配餐板上部 | THE SURFACE OF CABIN GALLEY G1 WORK COUNTER RIDGY REMARK:OVER THE SLIDING WORK TABLE | A20M2500506-1 | 500000345735 |  | 2014-05-02 10:17
客舱后厨房G22位置配餐板固定座丢失 | CABIN AFT GALLEY G22 LOCATION FOODTRAY BOTTOM MISSING | A20M2500506-1 | 500000345829 | 004079赵通 | 2014-05-01 15:49
客舱H厕所杂志盒破损 | THE RACK ASSY-MAGAZINE OF CABIN LAV H DAMAGED | A20M2500506-1 | 500000345876 | 001909伍文海 | 2014-05-01 17:12
客舱经济舱座椅脚保护盖破损,位置:R31 R32 R33 R35 R36 R37 R38 R39 R40 R41 R42 R43 R44 R46 R47 R48 R50 R54 R55 R56 R57,数量:76EA | THE CABIN E/C SEAT LEG COVER DAMAGED,LOCATION:R31 R32 R33 R35 R36 R37 R38 R39 R40 R41 R42 R43 R44 R46 R47 R48 R50 R54 R55 R56 R57,QTY:76EA | A20M2500506-1 | 500000346261 | 002796叶宇辉 | 2014-05-02 09:43
客舱经济舱座椅脚保护盖破损,位置:L32 L33 L34 L36 L37 L39 L40 L43 L44 L45 L46 L47 L49 L51 L55 L57,数量:36EA | THE CABIN E/C SEAT LEG COVER DAMAGED,LOCATION:L32 L33 L34 L36 L37 L39 L40 L43 L44 L45 L46 L47 L49 L51 L55 L57,QTY:36EA | A20M2500506-1 | 500000346269 | 002796叶宇辉 | 2014-05-02 09:45
客舱经济舱座椅杂志袋弹簧断裂:32B 35J 37B 40J 43CJ 46C 47C | THE CABIN E/C SEAT LITERATURE POCKET SPRING FRACTURED:32B 35J 37B 40J 43CJ 46C 47C | A20M2500506-1 | 500000346279 | 002796叶宇辉 | 2014-05-02 09:52
客舱经济舱座椅靠墙扶手装饰盖破损:46LR | THE OUTBOARD ARMREST COVERS OF THE CABIN E/C SEAT DAMAGED:46LR | A20M2500506-1 | 500000346284 | 002796叶宇辉 | 2014-05-02 10:03
客舱右后乘务员座椅头枕安装螺杆丢失1EA | THE RH AFT ATTENDANT SEAT HEADREST INSTALLATION BOLT MISSING,QTY:1EA | A20M2520512-1 | 500000346496 | 002257李锐明 | 2014-05-02 16:10
客舱头排座椅扶手前端盖板破损,座椅:31ABCHJK 35ABCHJK | THE FRONT COVERS ON CABIN IAT SEAT ARMREST DAMAGED,SEAT:31ABCHJK 35ABCHJK | A20M2500506-1 | 500000347358 | 002796叶宇辉 | 2014-05-03 14:04
客舱左右前隔板表面标牌破损。 | THE PLACARDS ON CABIN LH FWD AND RH FWD PARTITIONS SURFACE DAMAGED. | A20M2500506-1 | 500000347375 | 005696李浩荣 | 2014-05-03 14:13
客舱右隔板前表面墙纸破损。 | THE WALLPAPER ON CABIN RH FWD PARTITION FRONT SURFACE DAMAGED. | A20M2500506-1 | 500000347392 | 005696李浩荣 | 2014-05-03 14:25
客舱左右前隔板下部金属防踢板变形、凹坑,数量:2EA | THE LOWER METAL KICKSTRIPS ON CABIN LH FWD AND RH FWD PARTITIONS DEFORMED AND HAVE DENT,QTY:2EA | A20M2500506-1 | 500000347426 | 005696李浩荣 | 2014-05-03 15:00
客舱左右前隔板边缘铝装饰条表面划花。 | THE EDGE ALUMINIUM PROFILES SURFACE ON CABIN LH FWD AND RH FWD PARTITIONS SCRATCHED. | A20M2500506-1 | 500000347459 | 000504米远君 | 2014-05-03 15:25
客舱右2#门衬板标牌破损。(W446) | CABIN R2# PAX DOOR LINING PANEL PLACARD DAMAGED .(W446) | A20J711300-I2-1-A1 | 500000347950 | 004494潘宏达 | 2014-05-04 10:52
客舱A厕所标牌丢失,备注:PN:D2527706952300、D2527719957500 | THE PLACARD OF CABIN LAV A MISSING,REMARK:PN:D2527706952300、D2527719957500 | A20M2500506-1 | 500000348098 | 001909伍文海 | 2014-05-04 14:06
客舱左1#门门边板断裂,数量:1EA。 | THE DOORFRAME PANEL ON CABIN LH1# DOOR CRACKED,QTY:1EA. | A20M2500506-1 | 500000348148 | 000504米远君 | 2014-05-04 13:10
客舱行李架门复合材料破损,位置:R3(1EA),L35(3EA)L46(2EA)L57(2EA) | THE COMPOSITE MATERIAL ON CABIN STOWAGE BOX DOOR DAMAGED,LOC:R3(1EA),L35(3EA)L46(2EA)L57(2EA) | A20M2500506-1 | 500000348157 | 002207黄伟健 | 2014-05-04 13:15
客舱G1、G5、G8厨房烤箱螺丝锈蚀,备注:16EA | THE OVEN SCREWS OF CABIN GALLEY G1、G5、G8 CORROSIVE,REMARK:16EA | A20M2500506-1 | 500000348197 | 002270何智锋 | 2014-05-04 13:40
客舱前区灯箱板灯罩发黄,数量:2EA | THE LAMPCOVER ON CABIN FWD AREA LIGHT-BOX PANEL YELLOWING,QTY:2EA | A20M2500506-1 | 500000348241 | 002207黄伟健 | 2014-05-04 14:01
客舱前区灯箱板边缘封严条破损 | THE EDGE SEAL STRIP ON CABIN FWD AREA LIGHT-BOX PANEL DAMAGED. | A20M2500506-1 | 500000348251 | 004494潘宏达 | 2014-05-04 14:04
客舱头排座椅扶手掉漆,备注:46ABCJK、47H | THE PAINT COAT OF CABIN PASSENGER IAT SEAT ARMREST MISSING,REMARK:46ABCJK、47H | A20M2500506-1 | 500000349039 | 002796叶宇辉 | 2014-05-05 11:14
驾驶舱正、副驾驶座椅表面脏。 | THE SURFACE ON COCKPIT CAPTAIN AND F/O SEAT DIRTY. | A20M2500506-1 | 500000349496 | 002257李锐明 | 2014-05-05 16:01
驾驶舱副驾驶座椅升降滑轮保护盖破损。 | THE PROTECTIVE COVERS ON COCKPIT F/O SEAT LIFTING PULLEY DAMAGED. | A20M2500506-1 | 500000349502 | 002257李锐明 | 2014-05-05 16:05
前,左和右起落架勤务后,需5-10个起落后检查减震支柱压力 | AFTER 5-10 SREVICE LANDING,CHECK THE PRESSURE OF THE SHOCK STRUT WHEN NOSE,LH AND RH LDG GASEOUS SERVICING | A20M3221501-1 | 500000350299 |  | 2014-05-06 15:33
客舱后区灯箱板灯罩发黄(2EA) | CABIN AFT AREA LIGHT BOX LENS YELLOW (2EA) | NR/000000195 | 500000350316 | 004494潘宏达 | 2014-05-06 15:48
客舱后区灯箱板边缘封严条破损 | CABIN AFT AREA LIGHT BOX PANEL'S EDGE SEAL DAMAGED | NR/000000195 | 500000350318 | 004494潘宏达 | 2014-05-06 15:49
客舱右后门顶上天花板封严条破损 | CABIN AFT AREA RH DOOR UPPER CEILING PANEL'S SEAL DAMAGED | NR/000000195 | 500000350321 | 004494潘宏达 | 2014-05-06 15:50
客舱左一号门边框下部衬板边缘断裂 | CABIN RH 1# DOOR FRAME PANEL LOWER EDGE CRACK | NR/000000195 | 500000350323 | 004494潘宏达 | 2014-05-06 15:52
客舱行李箱门表面划伤,位置:L40 R1 R2 | CABIN OVERHEAD STOWAGE BIN DOOR SURFACE SCRATCH,LOC:L40 R1 R2 | 无/NONE | 500000350338 | 002207黄伟健 | 2014-05-06 16:00
客舱行李架门表面损伤,位置:L47 | THE SURFACE ON CABIN STOWAGE BIN DOOR DAMAGED,LOC:47 | A20M2500506-1 | 500000351452 | 002207黄伟健 | 2014-05-08 08:35
客舱行李箱门表面鼓起,备注:L3 R35 R56 L38 R38 R45 R46 L52 R52 L50 R53 R57 R54 R48 L46 | THE SURFACE OF CABIN OVERHEAD STOWAGE BIN DOOR BULGY,REMARK:L3 R35 R56 L38 R38 R45 R46 L52 R52 L50 R53 R57 R54 R48 L46 | A20M2500506-1 | 500000351789 | 000504米远君 | 2014-05-08 14:45
客舱A、H、D、E厕所通风滤棉脏 | THE AIR EXTRACTION FLEECE OF CABIN LAV A、H、D、E SMUDGY | A20M2500506-1 | 500000355716 | 001909伍文海 | 2014-05-13 10:18
驾驶舱门锁组件失效 | COCKPIT DOOR LATCH ASSY FAILED | A20J525111-01-1-1 | 500000356660 | 001909伍文海 | 2014-05-14 10:27
客舱G1厨房工作台表面鼓起。备注:配餐板上部 | THE SURFACE OF CABIN GALLEY G1 WORK COUNTER RIDGY REMARK:OVER THE SLIDING WORK TABLE | NR000001 | 500001057803 | 000664龚绍权 | 2016-03-07 10:57
按监控单B6339-1603-07,更换手提灭火瓶,P/N:74-20,S/N:13057 | REF MONITORING CARD B6339-1603-07,REPLACE PROTABLE FIRE EXTINGUISHER,P/N:74-20,S/N:13057 | 客户要求/CUSTOMER REQUIREMENT | 500001078895 | 000664龚绍权 | 2016-03-24 13:52
1C旅客座椅过道装饰板破损。 | THE OUTER ENDBAY SHROUD OF PAX SEAT #1C DAMAGED. | 预检项目/PRE-CHECK ITEM | 500001089348 | 000664龚绍权 | 2016-04-01 08:38
A厕所洗手台柜门破损。 | LAV A WASHBASIN DOOR ASSY DAMAGED. | 预检项目/PRE-CHECK ITEM | 500001089349 | 002366鲍春光 | 2016-04-01 08:41
H厕所洗手台柜门破损。 | LAV H WASHBASIN DOOR ASSY DAMAGED. | 预检项目/PRE-CHECK ITEM | 500001089350 | 002366鲍春光 | 2016-04-01 08:42
E厕所洗手台柜门破损 | LAV E WASHBASIN DOOR ASSY DAMAGED. | 预检项目/PRE-CHECK ITEM | 500001089351 | 002366鲍春光 | 2016-04-01 08:43
A厕所马桶坐垫破损。 | LAV A TOILET SEAT ASSY DAMAGED. | 预检项目/PRE-CHECK ITEM | 500001089352 | 005696李浩荣 | 2016-04-01 08:45
公务舱座椅过道装饰条有色差。 | OUTER SHROUDS OF BUSINESS CLASS SEAT CHROMATIC DEFECT. | 预检项目/PRE-CHECK ITEM | 500001089357 | 002366鲍春光 | 2016-04-01 08:51
E厕所马桶坐垫颜色不一致。 | LAV E TOILET SEAT ASSY CHROMATIC DEFECT. | 预检项目/PRE-CHECK ITEM | 500001089359 | 005696李浩荣 | 2016-04-01 08:54
行李箱上的R1,R2,L1,L2,L3座椅标牌盖破损。 | R1,R2,L1,L2,L3 SEAT NUMBER COVER ON THE OVERHEAD STOWAGE BIN DAMAGED. | 预检项目/PRE-CHECK ITEM | 500001089444 | 002366鲍春光 | 2016-04-01 09:18
H厕所镜子边缘掉色。 | THE EDGE OF LAV H MIRROR FADE. | 预检项目/PRE-CHECK ITEM | 500001089451 | 000664龚绍权 | 2016-04-01 09:21
D厕所镜子边缘掉色。 | THE EDGE OF LAV D FADE. | 预检项目/PRE-CHECK ITEM | 500001089453 | 000664龚绍权 | 2016-04-01 09:22
E厕所镜子边缘掉色。 | THE EDGE OF LAV E FADE. | 预检项目/PRE-CHECK ITEM | 500001089454 | 000664龚绍权 | 2016-04-01 09:23
1AC,1HK座椅扶手表面磨损。 | 1AC,1HK SEAT ARMCAP ASSY SURFACE WORN. | 预检项目/PRE-CHECK ITEM | 500001089469 | 002366鲍春光 | 2016-04-01 09:35
客舱左2#门乘务员座椅底板颜色不一致。 | BOTTOM PANEL OF ATTENDANT SEAT NEAR CABIN LEFT #2 DOOR CHROMATIC DEFECT. | 预检项目/PRE-CHECK ITEM | 500001089474 | 002366鲍春光 | 2016-04-01 09:44
防止固定式ELT意外触发,脱开ELT天线馈线插头,出厂前恢复。 | TO PREVENT FIXED ELT ACCIDENTAL TRIGGERING, DISCONNECT THE ELT ANTENNA COAX CONNECTOR, RESTORE NORMAL BEFORE FLIGHT. | 无/NONE | 500001089538 | 002366鲍春光 | 2016-04-01 10:31
左#1门的乘务员座椅表面掉漆。 | THE SURFACE OF ATTENDANT SEAT NEAR LEFT #1 DOOR FADED. | 预检项目/PRE-CHECK ITEM | 500001089558 | 002366鲍春光 | 2016-04-01 10:51
左#2门乘务员座椅表面掉漆。 | THE SURFACE OF ATTENDANT SEAT NEAR #2 DOOR FADED. | 预检项目/PRE-CHECK ITEM | 500001089560 | 002366鲍春光 | 2016-04-01 10:52
驾驶舱P7板掉漆 | COCKPIT P7 PANEL FINISH MISSING. | A20M-PRE-C-CHECK-IN | 500001089759 | 000504米远君 | 2016-04-01 12:57
D厕所洗手台柜门破损。 | LAV D WASHBASIN DOOR DAMAGED. | A20M2500506-1 | 500001089807 | 002366鲍春光 | 2016-04-01 13:23
客舱右#4门和左#1门乘务员座椅氧气面罩释放销及底座丢失。 | OXYGEN SYSTEM MASK MANUAL RELEASE TOOL AND BRACKET IN THE ATTENDANT SEAT NEAR CABIN DOOR R#4 AND L#1 MISSING. | A20M2500506-1 | 500001089834 | 002366鲍春光 | 2016-04-01 13:42
右#3门和左#1门乘务员座椅中的应急手电固定带断裂。 | FLASH COVERS IN THE R#3 AND L#1 ATTENDANT SEAT BROKEN. | A20M2500506-1 | 500001089853 | 000664龚绍权 | 2016-04-01 13:56
A,D,E厕所马桶罩松动。 | LAV A,D,E TOILET SHROUD LOOSEN. | A20M2500506-1 | 500001089864 | 002366鲍春光 | 2016-04-01 14:05
H厕所马桶罩颜色有差异。 | LAV H TOILET SHROUD CHROMATIC DEFECT. | A20M2500506-1 | 500001089889 | 002366鲍春光 | 2016-04-01 14:25
3AC和31ABC座椅之间行李箱门弹力不足。 | 3AC AND 31ABC OVERHEAD STOWAGE COMPARTMENT DOOR SPRING WEAK. | A20M2500506-1 | 500001089892 | 000664龚绍权 | 2016-04-01 14:29
客舱厨房烤箱螺丝锈蚀,备注:16EA | THE OVEN SCREWS OF CABIN GALLEY CORROSIVE,REMARK:16EA | A20M2500506-1 | 500001089936 | 000664龚绍权 | 2016-04-01 14:44
D厕所手提喇叭标牌破损。 | THE PLACARD "MEGAPHONE" ON LAV D DAMAGED. | A20M2500506-1 | 500001089954 | 002366鲍春光 | 2016-04-01 14:52
E厕所上的“烟灰缸在对面厕所”标牌破损。 | THE PLACARD "ASHTRAY ON THE OPPOSITE LAVATORY" ON THE LAV E DAMAGED. | A20M2500506-1 | 500001090004 | 002366鲍春光 | 2016-04-01 15:19
前,中,后厨房垃圾投放口标志掉漆。 | FWD,MID,AFT GALLEY WASTE FLAP PAINT FADED. | A20M2500506-1 | 500001090007 | 000504米远君 | 2016-04-01 15:22
46JK行李架内氧气输送管有孔。 | THERE IS A HOLE ON THE OXYGEN MASK PIPE IN THE 46JK OVER STOWAGE COMPARTMENT. | A20M2500506-1 | 500001090018 | 000664龚绍权 | 2016-04-01 15:28
前厨房配餐板地线接线片断。 | A GROUND WIRE TERMINAL OF FWD GALLEY FOODTRAY DAMAGED. | A20M2500506-1 | 500001090061 | 005501张洋 | 2016-04-01 15:46
前,后厨房配餐板固定装置丢失。3EA | FWD,AFT GALLEY SLIDING WORK TABLE RETAINER MISSING.3EA | A20M2500506-1 | 500001090122 | 000664龚绍权 | 2016-04-01 16:15
33K,58J座椅扶手胶皮破损。 | 33K,58J SEAT ARMREST COVER DAMAGED. | A20M2500506-1 | 500001090185 | 005501张洋 | 2016-04-01 16:55
49J,57J座椅餐板破损。 | FOODTRAY OF 49J,57J SEAT DAMAGED. | A20M2500506-1 | 500001090189 | 002366鲍春光 | 2016-04-01 16:57
客舱右前隔板下部金属面板翘起。 | THE LOWER METAL PLATE OF CABIN RH-FWD DIVIDER DEBOND. | A20M2500506-1 | 500001090190 | 000664龚绍权 | 2016-04-01 16:57
客舱PSU面板阅读灯不亮,位置:44D | CABIN PSU PANEL READING LIGHT FOUND NOT ILLUMINATE,LOCATION:44D | A20M2500506-1 | 500001090195 | 005501张洋 | 2016-04-01 16:59
2A,34ABC,34HJK,58HJK行李箱分隔板破损。 | 2A,34ABC,34HJK,58HJK OVERHEAD STOWAGE COMPARTMENT DIVIDER DAMAGED. | A20M2500506-1 | 500001090196 | 000504米远君 | 2016-04-01 16:59
46ABC行李箱门铰链固定锁片断裂。 | HINGE ASSY OF 46ABC OVERHEAD STOWAGE COMPARTMENT DOOR BROKEN. | A20M2500506-1 | 500001090200 | 000664龚绍权 | 2016-04-01 17:02
客舱行李箱门表面破损,备注:31ABC前 31HJK前 34ABC 35ABC 36ABC 35HJK 38HJK 38ABC 3AC 3HK 36HJK 43HJK 44HJK 44ABC 43ABC 46JK 47HJK 49HJK 50HJK 52ABC 58HJK 57HJK 58HJK后。 | THE SURFACE OF CABIN OVERHEAD STOWAGE BIN DOOR DAMAGED,REMARK:31ABC(FWD) 31HJK(FWD) 34ABC 35ABC 36ABC 35HJK 38HJK 38ABC 3AC 3HK 36HJK 43HJK 44HJK 44ABC 43ABC 46JK 47HJK 49HJK 50HJK 52ABC 58HJK 57HJK 58HJK(AFT)。 | A20M2500506-1 | 500001090201 | 002366鲍春光 | 2016-04-01 17:02
客舱旋转乘务员座椅电话底座螺丝丢失,数量:2EA | CABIN SWIVEL ATTENDANT SEAT HANDSET CRADLE SCREW MISSING,QTY:2EA | A20M2500506-1 | 500001090210 | 005501张洋 | 2016-04-01 17:06
客舱行李箱上部装饰条破损,备注:3HK. | THE UPER PANEL-COVER OF CABIN OVERHEAD STOWAGE BIN DAMAGED,REMARK:3HK. | A20M2500506-1 | 500001090223 | 000664龚绍权 | 2016-04-01 17:08
客舱的D,E厕所烟雾探测器盖破损 | CABIN LAV D,E SMOKE DETECTOR COVER DAMAGED | A20M2500506-1 | 500001090240 | 005501张洋 | 2016-04-01 17:20
客舱H厕所天花灯故障 | CABIN LAV H CEILING LIGHT FOUND FAULT | A20M2500506-1 | 500001090251 | 005501张洋 | 2016-04-01 17:26
拆装客舱FR42-FR47段的座椅,空气格栅,地毯与荧光条。 | REMOVE AND INSTALL THE SEAT,AIR GRILL,CARPET AND FLUORESCENT STRIP IN THE AREA OF CABIN FR42-FR47. | 20PANEL-240-1-1 | 500001090316 | 002366鲍春光 | 2016-04-01 20:04
拆装左后登机门上角内部衬板和隔热棉 | REMOVE AND INSTALL INNER LINING PANEL AND INSULATION BLANKET INSIDE THE LEFT AFT PASSAGER DOOR UPPER CORNER | A20J534132-01-4 | 500001090317 | 002366鲍春光 | 2016-04-01 20:18
方向舵钢索张力调节器指示超标 | CABLE TENSION REGULATOR OF RUDDER WAS OUT OF LIMIT | A20J272145-01-1 | 500001090740 | 002366鲍春光 | 2016-04-02 08:44
右4#门滑梯罩观察镜安装错误。 | RH 4# DOOR SLIDE COVER VIEWING PORT POSITION WRONG. | B32053038 | 500001090744 | 001150张灿 | 2016-04-02 08:47
841CZ衬板封严条脱胶。WIP76# | LINING PANEL 841CZ SEAL DISBOND. | 20PANEL-840-1-1 | 500001090883 | 001150张灿 | 2016-04-02 09:47
右1#门滑梯罩标牌破损。WIP73# | RH 1# DOOR SLIDE COVER PLACARD DAMAGED. | 20PANEL-840-1-1 | 500001090885 | 001150张灿 | 2016-04-02 09:49
左4#门滑梯罩防磨片一个螺杆和底座丢失。WIP74# | LH 4# DOOR SLIDE COVER BUMPER 1EA SCREW AND NUTPLATE MISSING. | 20PANEL-830-2-1 | 500001090886 | 001150张灿 | 2016-04-02 09:53
左4#门滑梯罩掉漆。WIP74# | LH 4# DOOR SLIDE COVER FINISH MISSING. | A20M-PRE-C-CHECK-MEC | 500001090894 | 000504米远君 | 2016-04-02 10:00
左1门天花应急灯不工作。 | EMERGENCY LIGHT ON THE CEILING PANEL NEAT LEFT #1 DOOR INOP. | A20M2500506-1 | 500001091166 | 005501张洋 | 2016-04-02 13:59
H和E厕所马桶漏水。 | H AND E LAV TOILET ASSY FOUND LEAKAGE. | A20M2500506-1 | 500001091219 | 005501张洋 | 2016-04-02 14:49
经济舱座椅行李架护栏堵盖丢失,位置:R41 R42 R43 R44 L41 L42 L43 L44 | E/C SEAT BAGGAGE TUBE PLUG MISSING,LOC:R41 R42 R43 R44 L41 L42 L43 L44 | A20MCABININSPECTION | 500001091277 | 004779刘国威 | 2016-04-02 15:17
经济舱座椅靠背后餐板破损,位置:41K 43K 43B 42A 41C 42K | E/C SEAT BACKREST REAR FOODTABLE DAMAGED,LOC:41K 43K 43B 42A 41C 42K | A20MCABININSPECTION | 500001091279 | 004779刘国威 | 2016-04-02 15:18
经济舱座椅行李架护栏松动,位置:R44 L44 L42 L41 | E/C SEAT BAGGAGE TUEB LOOSEN,LOC:R44 L44 L42 L41 | A20MCABININSPECTION | 500001091280 | 004779刘国威 | 2016-04-02 15:19
经济舱座椅作动筒控制钢索头卡阻,位置:44H | E/C SEAT HYDROLOCK CABLE KNOB JAMMED,LOC:44H | A20MCABININSPECTION | 500001091281 | 004779刘国威 | 2016-04-02 15:19
经济舱座椅救生衣袋拉绳丢失,位置:44C | E/C SEAT LIFE VEST POUCH STRIP MISSING,LOC:44C | A20MCABININSPECTION | 500001091283 | 004779刘国威 | 2016-04-02 15:20
经济舱座椅安全带锁扣失效,位置:43C | E/C SEAT BELT LOCK FAILED,LOC:43C | A20MCABININSPECTION | 500001091284 | 004779刘国威 | 2016-04-02 15:21
客舱A,D,E,H厕所内马桶盖标牌丢失。 | THE PLACARD ON THE TOILET SHROUD OF CABIN LAVATORY MISSED. | A20M2500506-1 | 500001091287 | 005696李浩荣 | 2016-04-02 15:23
客舱A,D,E,H厕所内马桶罩组件表面破损。 | THE TOILET SHROUD ASSY SURFACE OF CABIN LAVATORY DAMAGED. | A20M2500506-1 | 500001091290 | 005696李浩荣 | 2016-04-02 15:25
清洁乘务员座椅:左前,右前,H厕所前. | CLEAN ATTENDANT SEAT:LH FWD,RH FWD,LAV H FWD. | A20MCABININSPECTION | 500001091291 | 001362欧阳军梅 | 2016-04-02 15:26
清洁客舱厕所内马桶罩组件,数量:4EA。 | CLEAN THE TOILET SHROUD ASSY OF THE CABIN LAVATORY,QTY:4EA. | A20M2500506-1 | 500001091292 | 005696李浩荣 | 2016-04-02 15:27
乘务员座椅标牌损坏:左前,右前,H厕所前. | THE PLACARDS OF ATTENDANT SEATS BROKEN:LH FWD,RH FWD,LAV H FWD. | A20MCABININSPECTION | 500001091293 | 001362欧阳军梅 | 2016-04-02 15:28
左前乘务员座椅坐垫板固定转轴松 | THE AXIS OF LH FWD ATTENDANT SEAT PAN LOOSEN. | A20MCABININSPECTION | 500001091294 | 001362欧阳军梅 | 2016-04-02 15:29
经济舱座椅脚脏,位置:L41-L44,R41-R44。 | THE CABIN E/C SEAT FOOT DIRTY,LOC:L41-L44,R41-R44. | A20M2500506-1 | 500001091296 | 004779刘国威 | 2016-04-02 15:30
乘务员座椅上靠背防磨片断裂,数量:3EA,位置:左前,H厕所前 | THE PROTECTION PLATE OF ATTENDANT SEAT UPPER BACKREST BROKEN,QUANTITY:3EA,LOCATION:LH FWD,LAV H FWD. | A20MCABININSPECTION | 500001091297 | 001517周孔颖 | 2016-04-02 15:31
客舱经济舱座椅靠背不平,位置:L41-L44,R41-R44。 | THE BACKREST OF THE CABIN E/C SEAT NOT IN LINE,LOC:L41-L44,R41-R44. | A20M2500506-1 | 500001091298 | 004779刘国威 | 2016-04-02 15:31
H厕所前乘务员座椅上靠背板裂:1EA | LAV H FWD ATTENDANT SEAT UPPER BACKREST PANEL BROKEN:1EA. | A20MCABININSPECTION | 500001091299 | 001517周孔颖 | 2016-04-02 15:31
客舱经济舱座椅餐板不平,位置:L41-L44,R41-R44。 | THE FOODTRAY OF THE CABIN E/C SEAT NOT IN LINE,LOC:L41-L44,R41-R44. | A20M2500506-1 | 500001091300 | 004779刘国威 | 2016-04-02 15:33
乘务员座椅上靠背套,下靠背套,坐垫套破损,数量:9EA,位置:左前,右前,H厕所前 | THE UPPER BACKREST/LOWER BACKREST/BOTTOM COVER BROKEN,QUANTITY:9EA,LOCATION:LH FWD,RH FWD,LAV H FWD. | A20MCABININSPECTION | 500001091301 | 001362欧阳军梅 | 2016-04-02 15:33
乘务员座椅安全带磨损,数量:3EA,位置:左前,右前,H厕所前 | THE SAFETY BELT OF ATTENDNAT SEAT WORN,QUANTITY:3EA,LOCATION:LH FWD,RH FWD,LAV H FWD. | A20MCABININSPECTION | 500001091302 | 001362欧阳军梅 | 2016-04-02 15:35
经济舱座椅扶手松动,位置:41JR 44J | E/C SEAT ARMREST LOOSEN,LOC:41JR 44J | A20MCABININSPECTION | 500001091327 | 004779刘国威 | 2016-04-02 16:01
左1号门内侧乘务员座椅下部柜门破损 | LH 1# DOOR INBOARD ATTENDANT SEAT LOWER DOOR BROKEN | A20MCABININSPECTION | 500001091903 | 001362欧阳军梅 | 2016-04-03 09:34
客舱后区灯箱板灯罩发黄,共2EA | CABIN AFT ZONE LIGHT COVER LENS AGING,2EA. | A20MCABININSPECTION | 500001091918 | 001150张灿 | 2016-04-03 09:42
客舱前后区灯箱板快卸螺钉缺失,共9EA. | CABIN FWD/AFT ZONE LIGHT COVER STUD MISSING,9EA. | A20MCABININSPECTION | 500001091920 | 001150张灿 | 2016-04-03 09:42
客舱后区灯箱板封严胶皮磨损。 | CABIN AFT ZONE LIGHT COVER EDGE-SEAL WORN. | A20MCABININSPECTION | 500001091922 | 001150张灿 | 2016-04-03 09:43
客舱7#天花板边缘处断裂. | CABIN 7# CEILING PANEL EDGE CRACKED. | A20MCABININSPECTION | 500001091924 | 000504米远君 | 2016-04-03 09:44
客舱L1#门下部门框衬板表面破损,共2EA | CABIN L1# DOOR LOWER FRAME LINING PANEL SURFACE DAMAGED,2EA. | A20MCABININSPECTION | 500001091925 | 000504米远君 | 2016-04-03 09:44
清洁客舱行李箱门.共22EA | CLEAN CABIN OVERHEAD STOWAGE BIN DOOR, QTY 22EA | A20M2500506-1 | 500001091945 | 002799李健 | 2016-04-03 10:23
清洁客舱门框衬板及下天花板.共15EA | CLEAN CABIN DOOR FRAME LINING PANELS AND LOWER CEILING PANELS,QTY:15EA | A20M2500506-1 | 500001091946 | 002799李健 | 2016-04-03 10:24
正驾驶员大扶手作动筒失效 | CAPTAIN SEAT BIG ARMREST ACTUATOR DISABLED | A20MCABININSPECTION | 500001092064 | 001517周孔颖 | 2016-04-03 11:02
副驾驶座椅大扶手作动筒失效 | F/O SEAT BIG ARMREST ACTUATOR DISABLED | A20MCABININSPECTION | 500001092065 | 001517周孔颖 | 2016-04-03 11:02
正、副驾驶员座椅大扶手支架掉漆 | CAPTAIN & F/O SEAT BIG ARMREST SUPPORT PAINT PEEL OFF | A20MCABININSPECTION | 500001092069 | 001362欧阳军梅 | 2016-04-03 11:03
副驾驶座椅小扶手下装饰板破损 | F/O SEAT SMALL ARMREST LOWER SHROUD BROKEN | A20MCABININSPECTION | 500001092070 | 001362欧阳军梅 | 2016-04-03 11:04
正、副驾驶员座椅安全带磨损 | CAPTAIN & F/O SEAT SAFETY BELT ABRASION | A20MCABININSPECTION | 500001092076 | 001362欧阳军梅 | 2016-04-03 11:10
副驾驶员座椅控制手柄装饰盒破损 | F/O SEAT CONTROL HANDLE BOX BROKEN | A20MCABININSPECTION | 500001092081 | 001362欧阳军梅 | 2016-04-03 11:13
清洁正、副驾驶员座椅 | CLEAN CAPTAIN & F/O SEAT | A20MCABININSPECTION | 500001092086 | 001517周孔颖 | 2016-04-03 11:20
正驾驶坐垫下部灯故障 | CAPTAIN SEAT PAN LOWER LIGHT INOP | A20MCABININSPECTION | 500001092087 | 001362欧阳军梅 | 2016-04-03 11:21
正、副驾驶员座椅底座滑轮保护盖丢失,3EA | CAPTAIN & F/O SEAT BASE PULLEY COVER MISSING,3EA | A20MCABININSPECTION | 500001092089 | 001517周孔颖 | 2016-04-03 11:23
副驾驶员座椅后下部装饰板破损变形 | F/O SEAT BACKREST REAR LOWER FAIRING DEFORMED , BROKEN | A20MCABININSPECTION | 500001092093 | 001362欧阳军梅 | 2016-04-03 11:24
H和D厕所洗手池排水滤芯丢失。 | THE FILTER ASSY OF LAV H & D WASHBASIN MISSING. | A20M2500506-1 | 500001096422 | 002366鲍春光 | 2016-04-06 15:23
D和E厕所冲洗活门通气软管丢失。 | FLUSH VALVE TUBING OF LAV D & E TOILET MISSING. | A20M2500506-1 | 500001096465 | 002366鲍春光 | 2016-04-06 15:50
驾驶舱装饰板储物柜/盒杯托脏 | COCKPIT DECORATIVE PANELS, STORAGE BOXES / CABINETS AND CUP HOLDER ARE DIRTY. | A20J341300-13-1 | 500001098041 | 005501张洋 | 2016-04-08 15:03
客舱后应急喇叭脏。 | IN CABIN AFT EMERGENCY MEGAPHONE DIRTY. | A20J341300-13-1 | 500001098042 | 005501张洋 | 2016-04-08 15:00
客舱旅客座椅右37,44位置天花灯不工作。 | CABIN PAX SEAT POS R37 AND R44 CEILING LIGHTS INOP. | A20M2500506-1 | 500001098640 | 005501张洋 | 2016-04-08 09:08
客舱旅客座椅左1,4位置天花灯不工作。 | CABIN PAX SEAT POS L1 AND L4 CEILING LIGHTS INOP. | A20M2500506-1 | 500001098681 | 005501张洋 | 2016-04-08 09:29
客舱左47行李箱内缺少婴儿救生衣。6EA | 6EA LIFE VEST OF INFANTS IN CABIN OVERHEAD STOWAGE COMPARTMENT L47 MISSING. | A20M2500506-1 | 500001099131 | 002366鲍春光 | 2016-04-08 13:31
客舱后厨房4#烤箱故障。 | CABIN AFT GALLEY #4 OVEN FAULT. | 无/NONE | 500001100126 | 005501张洋 | 2016-04-09 10:38